## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: Agroasist | [6 empty] | INSTUTUTE & DEPARTMENT NAME: | [11 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(CSE-Data Science)
PROJECT GUIDE: Prof.Swati P | [6 empty] | DATE: | [11 empty] | 2026-04-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [34 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Piyush sase,Harsh Sarwankar,satyam patel,pushkar patole | 2026-01-13 | 2026-01-16 | 1 | 100% | WEEK 1 W: Project planning, team formation, and idea finalization for the Agro Assist application
1.2 | Identifying the functionalities of the Mini Project | piyush sase,satyam patel | 2026-01-16 | 2026-01-20 | 1 | 100% | WEEK 2 T: Problem identification, requirement gathering, and defining objectives for Agro Assist
1.3 | Discussing the project topic with the help of paper prototype. | Harsh Sarwankar,piyush sase,Satyam patel | 2026-01-20 | 2026-02-03 | 2 | 100% | WEEK 3 F: System design including workflow, architecture, UI/UX planning, and database/API structure design
1.4 | Designing the Graphical User Interface(GUI) | Satyam patel | 2026-02-03 | 2026-02-17 | 2 | 100% | WEEK 6 T: Backend development using Django REST API and frontend setup using Flutter (basic UI screens and navigation)
1.5 | Presentation I | Piyush ,satyam,pushkar,harsh | 2026-02-17 | 2026-02-24 | 1 | 100% | WEEK 6 T: Development of crop recommendation module based on season, soil type, and land inputs
2 | Project Design and Implementation
2.1 | Database Design | Satyam ,Harsh | 2026-02-24 | 2026-03-10 | 2 | 100% | WEEK 6 M: Integration of step-by-step crop guide, weather updates, and input calculation features (seeds, fertilizers, water)
2.2 | Database Connectivity of all modules | Satyam , pushkar | 2026-03-10 | 2026-03-17 | 1 | 100% | WEEK 7 W: Testing and debugging of all modules to ensure smooth and error-free performance
2.3 | Integration of all modules and Report Writing | Pushkar,Harsh | 2026-03-17 | 2026-03-24 | 1 | 100% | WEEK 6 F: Final integration of frontend and backend with performance optimization and UI improvements
2.4 | Presentation II | Piyush,Pushkar,Satyam,Harsh | 2026-03-24 | 2026-04-01 | 1 | 100% | WEEK 7 M: Documentation preparation, report writing, and final presentation & submission of Agro Assist