## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: Coffee Shop Management System | [6 empty] | INSTUTUTE & DEPARTMENT NAME: | [11 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(CSE-Data Science)
PROJECT GUIDE: Avinash Shrivas | [6 empty] | DATE: | [11 empty] | 2026-04-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [34 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Parth,Suhrud,Harish,Manthan | 2026-01-13 | 2026-01-16 | 1 | 100% | WEEK 1 M: Defined the Problem Statement and set core Objectives such as order management, billing, inventory tracking, and sales reports.
1.2 | Identifying the functionalities of the Mini Project | parth | 2026-01-16 | 2026-01-20 | 1 | 100% | WEEK 2 M: Finalized the System Architecture, choosing Flutter for the frontend and Firebase/Node.js for the backend and database.
1.3 | Discussing the project topic with the help of paper prototype. | Manthan,Harish,Parth,Suhrud | 2026-01-20 | 2026-02-03 | 2 | 100% | WEEK 3 M: Designed wireframes for the coffee shop management system including login page, menu management, order screen, billing page, and admin dashboard.
1.4 | Designing the Graphical User Interface(GUI) | Parth | 2026-02-03 | 2026-02-17 | 2 | 100% | WEEK 5 M: conducted an in-depth literature survey on existing coffee shop and restaurant management systems to understand current features and technologies used
1.5 | Presentation I | Parth,Harish,Suhrud,Manthan | 2026-02-17 | 2026-02-24 | 1 | 100% | WEEK 7 M: started working on designing UI and successfully made the Home page, Dashboard
2 | Project Design and Implementation
2.1 | Database Design | Parth,Manthan | 2026-02-24 | 2026-03-10 | 2 | 100% | WEEK 8 M: Added the menu and also added the too many options on coffee; WEEK 9 M: Integrated the Firebase Cloud Messaging (FCM) notification service for push alerts on requests and status updates.
2.2 | Database Connectivity of all modules | Parth,Harish | 2026-03-10 | 2026-03-17 | 1 | 100% | WEEK 10 M: now generated the order & billing system and also analyzed sales report
2.3 | Integration of all modules and Report Writing | Suhrud,Harish | 2026-03-17 | 2026-03-24 | 1 | 100% | WEEK 11 M: Conducted End-to-End testing of the app and app is working but sir told to update some other features or some attractiveness
2.4 | Presentation II | Parth, Manthan,Suhrud | 2026-03-24 | 2026-04-01 | 1 | 100% | WEEK 12 M: finally the firebase is connected and app app is now fully functional